## Test plan
Test Plan
Project name | File Uploader Testing
Application | File Uploader
System Under Test | https://the-internet.herokuapp.com/upload
Project Objective | Verify that user can select and upload files successfully using the available file selection methods.
Testing Objective | Verify file selection functionality.
Verify file upload functionality.
Verify file selection by clicking the upload area.
Verify drag-and-drop functionality.
Verify uploading different file types.
Verify system behavior when no file is selected.
Verify basic error handling.
Identify functional defects.
In Scope | File selection using Choose File
File selection using the upload area
File upload using the Upload button
Drag-and-drop file selection and upload
Uploadind different file types
Upload attempt without selecting a file
Basic error handling
Out of Scope | Performance testing
Cross-browser testing
File size limit testing
Test Environment
OS | macOS 26.5.1 (25F80)
Browser | Chrome Version 154.0.8037.98 (Official Build) (arm64)
Test Approach | Checklist-based
Testing types | Functional, UI, Negative testing

## Q&A
ID | Question
Q001 | Which file formats are supported by the File Uploader?
Q002 | Is there a maximum file size limit?
Q003 | Is multiple file upload supported, or can users upload only one file at a time?
Q004 | What should happen when the Upload button is clicked without selecting a file?
Q005 | Are there any file types that should not be accepted by the File Uploader?
Q006 | Should an error message be displayed when a user upload an unsupported file?
Q007 | What should happen after a file is uploaded successful?
Q008 | Should the uploaded file name be displayed after a successful upload?
Q009 | Are there any restrictions on file names, such as length, spaces, or special characters?

## Test Data
Test Data
Test Data ID | File Name | Format | Purpose
TD001 | test.txt | TXT | Standard text file
TD002 | test.pdf | PDF | PDF file
TD003 | test.jpg | JPG | Image file
TD004 | empty.txt | TXT | Empty file
TD005 | test.exe | EXE | Executable file
TD006 | test.zip | ZIP | Archive file
TD007 | file with spaces.txt | TXT | File name containing spaces
TD008 | special_#file.txt | TXT | File name containing a special character

## Checklist
Checklist ID | Category | Description | Priority | Test Data
CFU001 | UI | Verify that the File Uploader page is displayed correctly | High | -
CFU002 | UI | Verify that the Choose File button is displayed correctly | High | -
CFU003 | UI | Verify that the Upload button is displayed | High | -
CFU004 | Functional | Verify that the file selection dialog opens after clicking Choose File | High | -
CFU005 | Functional | Verify that a file can be selected using Choose File | High | TD001
CFU006 | Functional | Verify that the selected file name is displayed | High | TD001
CFU007 | Functional | Verify that a file selected using Choose File can be uploaded successfully | High | TD001
CFU008 | Functional | Verify that the file selection dialog opens when the upload area is clicked | High | -
CFU009 | Functional | Verify that a file selected via the upload area can be uploaded successfully | High | TD001
CFU010 | Functional | Verify that a file can be selected by dragging and dropping it into the upload area | High | TD001
CFU011 | Functional | Verify that a file selected via drag-and-drop can be uploaded successfully | High | TD001
CFU012 | Negative | Verify system behavior when Upload is clicked without selecting a file | High | -
CFU013 | Functional | Verify that different file types can be selected and uploaded using Choose File | Medium | TD001, TD002, TD003, TD005, TD006
CFU014 | Functional | Verify that an empty file can be uploaded | Medium | TD004
CFU015 | Functional | Verify that a file with spaces in its name can be uploaded | Medium | TD007
CFU016 | Functional | Verify that a file with a special character in its name can be uploaded | Medium | TD008
CFU017 | Functional | Verify that the uploaded file name is displayed correctly after a successful upload | High | TD001

## Test Run AM_13.08
Checklist ID | Test Data | Expected Result | Actual Result | Status | Bug ID
CFU001 | - | The File Uploader page is displayed correctly | The File Uploader page is displayed correctly | Pass
CFU002 | - | The Choose File button is displayed correctly | The Choose File button is displayed correctly | Pass
CFU003 | - | The Upload button is displayed | The Upload button is displayed | Pass
CFU004 | - | The file selection dialog opens after clicking Choose File | The file selection dialog opens after clicking Choose File | Pass
CFU005 | TD001 | The file can be selected using Choose File | The file is selected using Choose File | Pass
CFU006 | TD001 | The selected file name is displayed correctly | The selected file name is displayed correctly | Pass
CFU007 | TD001 | The file selected using Choose File is uploaded successfully | Choose File is uploaded successfullyThe file selected using Choose File is uploaded successfully | Pass
CFU008 | - | The file selection dialog opens when the upload area is clicked | The file selection dialog opens when the upload area is clicked | Pass
CFU009 | TD001 | The file selected via the upload area is uploaded successfully | An Internal Server Error is displayed instead of successfully uploading the selected file. | Fail | BR-FU01
CFU010 | TD001 | The file can be selected by dragging and dropping it into the upload area | The file is selected by dragging and dropping it into the upload area | Pass
CFU011 | TD001 | The file selected via drag-and-drop is uploaded successfully | An Internal Server Error is displayed instead of successfully uploading the selected file. | Fail | BR-FU02
CFU012 | - | The system handles an upload attempt without a selected file without a server error | An Internal Server Error is displayed | Fail | BR-FU03
CFU013 | TD001, TD002, TD003, TD005, TD006 | Different file types can be selected and uploaded successfully using Choose File | Different file types are selected and uploaded successfully using Choose File | Pass
CFU014 | TD004 | The empty file can be uploaded successfully | - | Not Run
CFU015 | TD007 | The file with spaces in its name can be uploaded successfully | - | Not Run
CFU016 | TD008 | The file with a special character in its name can be uploaded successfully | - | Not Run
CFU017 | TD001 | The uploaded file name is displayed correctly after a successful upload | - | Not Run

## Bug Reports
ID: | BR-FU01 | BR-FU02 | BR-FU03
Title: | Internal Server Error occurs when uploading a file selected via the upload area | Internal Server Error occurs when uploading a file selected via drag-and-drop | Internal Server Error occurs when Upload is clicked without selecting a file
Preconditions | The File Uploader page is open. | The File Uploader page is open and a test file is available on the desktop. | The File Uploader page is open and no file is selected.
Reproduction steps: | 1. Click inside the drag-and-drop upload area. | 1.Drag a file from the desktop. | 1. Do not select a file.
| 2. Select a file from the file selection dialog. | 2.Drop the file into the drag-and-drop upload area. | 2.Click the Upload button.
| 3. Click the Upload button. | 3. Click the Upload button.
Expected result: | The selected file is uploaded successfully and the uploaded file name is displayed. | The selected file is uploaded successfully and the uploaded file name is displayed. | The system should handle the upload attempt gracefully without displaying a server error.
Actual result: | An Internal Server Error is displayed instead of successfully uploading the selected file. | An Internal Server Error is displayed instead of successfully uploading the selected file. | An Internal Server Error is displayed.
Priority | High | High | Medium
Severity | Major | Major | Major
Environment | OS: macOS 26.5.1 (25F80) | OS: macOS 26.5.1 (25F80) | OS: macOS 26.5.1 (25F80)
| Browser: Chrome Version 154.0.8037.98 (Official Build) (arm64) | Chrome Version 154.0.8037.98 (Official Build) (arm64) | Chrome Version 154.0.8037.98 (Official Build) (arm64)
Attachments: